## Sheet1
Sprint | Ticket | Issue Description | Acceptance Criteria | Developer | DB QA Required | QA | Current Status | % Complete | Dev Complete | QA Complete | UAT Complete | Regression Complete | Release Date | Comments/Action Items
Jun 2 Release | GP-2194 | US Tax Migration for Historical Orders and Returns | US Tax Migration for Historical Orders and Returns. | Radha | Y | Nand | QA
Jun 2 Release | ECOM-7129 | Return-Only functionality from Hybris to RFO | For any combination of return ONLY items (Shipping, Handling, Product Tax, Shipping Tax or Handling Tax), Hybris or Boomi needs to translate this into a single product SKU [RTNTSH1-01] item on the return data into RFO. | Rama | Y |  | QA |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 - will be merged in STG-2 Thursday a.m.
Jun 2 Release | ECOM-6678 (ECOM-6801) | CID is different in Litle than in RFO | CID in Litle/AMEX is the same as CID on the order in RFO/Hybris | Bhushan | ? | Mandeep | QA |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 - will be merged in STG-2 Thursday a.m.
Jun 2 Release | (GP-939) MAIN-4487 | All orders should have shipping address | All orders have shipping address --1761341 missing liabilty issue for product recall. Can't be used for fraud dedection. Should be auditable. "SELECT COUNT(*) FROM Hybris.Orders o JOIN hybris.orderitem oi ON oi.OrderId = o.OrderID AND oi.ProductID NOT IN (175,176,8796151480321) WHERE NOT EXISTS (SELECT * FROM Hybris.OrderShippingAddress WHERE OrderID = o.OrderID) --1761341" | Johnny | Y | TBD | Dev |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 pm - will go live with updates that can only be made systematically. Shipping/Billing impact analysis on ECC impact to be done for tickets that cannot be updated systematically - Johnny/Prashanti/Sowshilya (send those missing zip and state).
Jun 2 Release | (GP-2088) MAIN-4486 | RFO Prod Push: Order Addresses Missing Attributes | Address validation in RFL on zipcode, state and city. On all existing Billing, Shipping and Main address types and also validation going forward. Restrict QAS Override for address validation | Manoj | Y | TBD | Dev |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 pm - will go live with updates that can only be made systematically. Shipping/Billing impact analysis on ECC impact to be done for tickets that cannot be updated systematically - Johnny/Prashanti/Sowshilya (send those missing zip and state).
Jun 2 Release | II-1834 | (Feature) Litle communication timeouts | Proposed Solution: Provide a report with Order ID, Transaction ID, Amount, Account for missing transactions. | Johnny | ? | TBD | Dev |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 pm - Experiencing issues with FTP connection. Johnny to sync with Lisa. Working when tested locally.
Jun 2 Release | II-1830 | (Feature) We need to enable functionality that allows Shipping only or tax only refunds through the regular return interface in NSCore | The ability to return Tax only, S&H only, and S&H/tax only through Heirloom, so we have an appropriate ReturnOrder for VTRequest refunds. | Jose | Y | Wendy | Dev |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 pm - dev changes in progress, Johnny to get update from Jose.
Jun 2 Release | MAIN-4373 | Order total != payment total | Order total and payment total should always match | Jose | Y | TBD | QA |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 - dev complete. Ready for QA. Johnny to provide Viktor orders w/wrong tax amt
Jun 2 Release | MAIN-4372 | Order header total != item sum | The order and item level totals match | Jose | Y | TBD | QA |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/23 - dev complete. Ready for QA.
Jun 2 Release | II-1833 | (Feature) Ability to update missing Litle transaction IDs in database | We need to enable manual update of TransactionID on such orders in order to be able to return against them. | Harold | Y | TBD | QA |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/23 - dev complete. Ready for QA.
Jun 2 Release | ECOM-7133 | Order exists in Hybris DB and RFO within the Hybris.Orders table . |  | Ganesh | Y | TBD | Dev |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 - dev and unit testing complete on TST3, needs to be unit tested in STG2 on Thursday.
Jun 2 Release | GP-2013 | Orders in RFO with unsupported VendorID | VendorID mapping in RFO matches the Credit Card vendors on orders in Litle | Manoj | Y | TBD | Dev |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 pm - Manoj to connect with downstream systems to discuss impact.
Jun 2 Release | ECOM-7119 | Order notes disappears in RFO db | Order notes should be present on the order note table on the RFO | Ganesh (Sowshilya, Radha) | Y | TBD | Dev |  | 2016-05-24 | 2016-05-26 | 2016-05-31 | 2016-05-27 | 2016-06-02 | 5/24 pm - on track to complete dev by EOD.